## Sheet1
[Company Name]
[Facility/Site Name] | Community Benefits Engagement Plan
Last updated: | Insert date here when updated
Area | Action | Implementation Tips | Status | Responsible party | Start date | Due date | Site-specific Implementation notes | Initial next steps | Status Update Notes
Ready your organization | Assess internal capacity & select the team for benefits planning | - Sustainability, community affairs, economic affairs, facility development or other internal functions are reasonable candidates to lead an engagement approach | Completed |  | mm/dd/yyyy | mm/dd/yyyy
| Buy-in from leadership and key departments | - What are points of alignment between the company's mission and values? - What business imperatives can be advanced through community support? - What are the risks of inaction (such as development delays)? | Completed |  | mm/dd/yyyy | mm/dd/yyyy
| Understand the company’s reputation with community | - How is the company perceived by workers and community members? - Any community initiatives already in place? | Delayed |  | mm/dd/yyyy | mm/dd/yyyy
| Partner with intermediaries | - Suggestions for how to choose an intermediary provided in the resource library | In Progress |  | mm/dd/yyyy | mm/dd/yyyy
Develop an understanding of community context | Complete a community power mapping exercise | - An example power mapping exercise is available in Appendix X of the Community Benefits Handbook | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Identify information sources for community composition, history and context | - Pursue all potential sources of information - Common sources include archives, local journalists, non-profit leaders, chambers of commerce, unions, local governmental, and community groups | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Develop a standard list of questions to capture community context and local histories |  | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Determine research method for pursuing each source | - Research methods include desktop research, individual interview, group interview, community survey, and GIS-based analysis | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Synthesize results to inform engagement strategy | - Leveraging these results is essential to successful community engagement | Not started |  | mm/dd/yyyy | mm/dd/yyyy
Conduct an enviornmental health community impact and preliminary needs assessment | Identify community health and climate risk vulnerabilities | - Use existing databases and desktop research - Suggested resources are linked in the community benefits handbook | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Leverage existing needs assessments | - Helpful resources include local climate action, economic development, or pollution reduction plans | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Determine development impact on existing vulnerabilities | - Leverage the 'Technology-specific Risks' anlsysis in Appendix XX in the Community Benefits Handbook | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Identify groups working to address vulnerabilities | - Groups likely include non-profit and non-governmental organizations - Leverage the community leaders as a starting point | Not started |  | mm/dd/yyyy | mm/dd/yyyy
Intentionally engage stakeholders | Define a North Star for your Engagement Efforts | -Build strong relationships - Process should be inclusive and equitable | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Situate the Coalition or Anchor Partners | - First determine if an existing coalition of community leaders already exists; leverage existing groups if at all possible - Ensure coalitions are diverse and representative of all community members | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Begin Convening | - Be transparent about your intentions, early project details, expectations, and asks | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Involve the Broader Community | - Strive to reach Level 3 or higher the Spectrum of Community Engagement to Ownership | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Align benefits planning with coalition decision-making processes | - Listen more than you speak - Be transparent about engagement efforts - Proactively address grievances | Not started |  | mm/dd/yyyy | mm/dd/yyyy
Co-develop community benefits plans | Draft a community benefits concept for the project | - Use the environmental impact and community needs assessment, as well as community feedback | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Work through a menu of benefits options | - See Appendix XX for a sample menu of potential benefits - Benefits list is not exhaustive, and companies should leave space for co-creation with community members | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Decide on an agreement vehicle and accountability process | - Many agreement vehicles (both legally binding and not) - Make a decision with the community - Legally binding agreements are best | Not started |  | mm/dd/yyyy | mm/dd/yyyy
| Draft and refine agreement documents | - One sided agreement drafting can create tension - Ensure the agreements are two-way, and have carve outs for continued improvement over time | Not started |  | mm/dd/yyyy | mm/dd/yyyy